## Project Title

Explainable AI–Based Detection of Pediatric Cardiovascular Diseases Using Multi-Lead ECG Signals

## Problem Statement

Pediatric cardiovascular diseases often present subtle and age-dependent electrocardiographic patterns that are difficult to interpret consistently using conventional diagnostic approaches. While recent advances in artificial intelligence have demonstrated promising results in ECG-based disease detection, most existing models are adult-centric and operate as black boxes, offering limited interpretability. There is a critical need for pediatric-specific, explainable AI models that not only classify cardiovascular diseases from ECG signals but also provide clinically meaningful explanations of their decisions to support trust, validation, and adoption in pediatric healthcare settings.

## Motivation

Electrocardiography is a widely used, non-invasive diagnostic tool in pediatric cardiology; however, ECG interpretation in children is more complex than in adults due to developmental changes in cardiac physiology and waveform morphology. The availability of a large, well-annotated pediatric ECG dataset with disease-level labels provides a unique opportunity to investigate disease-specific ECG patterns using AI. Integrating explainable AI techniques into this analysis is essential to bridge the gap between model predictions and clinical reasoning, enabling clinicians to understand which ECG components contribute to automated decisions. This work aims to advance trustworthy AI for pediatric cardiovascular diagnostics while maintaining strong biomedical interpretability.

## Objectives

- To preprocess and analyze multi-lead pediatric ECG signals for selected cardiovascular diseases.

- To develop supervised deep learning models for detecting pediatric cardiovascular diseases from ECG data.

- To apply explainable AI techniques to interpret model predictions at the ECG waveform level.

- To study age-dependent variations in ECG-based disease detection and model explanations.

- To evaluate model performance, robustness, and failure cases in clinically relevant scenarios.

## Expected Deliverables

- Cleaned and curated pediatric ECG subsets for selected diseases.

- Trained deep learning models for disease classification.

- Explainability visualizations highlighting ECG regions influencing predictions.

- Age-wise comparative analysis of model behavior and explanations.

- A complete experimental pipeline with documented code and results.

- A manuscript-ready set of figures, tables, and methodological descriptions suitable for Q1 journal submission.

| Week | Tasks | Goal | Expected Outcome |
| --- | --- | --- | --- |
| Week 1 | Introduction to ECG fundamentals; study pediatric ECG physiology; overview of cardiovascular diseases | Establish biomedical foundation | Clear understanding of ECG waves and pediatric disease context |
| Week 2 | Dataset exploration; visualization of raw ECG signals; understanding leads and labels | Familiarization with dataset | ECG plots with disease annotations and descriptive notes |
| Week 3 | Comparative analysis of normal vs diseased ECGs; qualitative waveform observations | Develop signal interpretation skills | Documented ECG pattern differences |
| Week 4 | Feature awareness: heart rate, intervals, waveform durations; basic signal metrics extraction | Link ECG features to physiology | Feature tables with biomedical interpretation |
| Week 5 | Development of baseline deep learning classifier (binary or limited multiclass) | Build initial predictive model | Working classification model with baseline metrics |
| Week 6 | Integration of explainable AI techniques (e.g., saliency maps, Grad-CAM) | Enable interpretability | ECG-level explanation visualizations |
| Week 7 | Age-group stratification; performance and explanation comparison across age ranges | Pediatric-specific insight | Age-wise analysis plots and observations |
| Week 8 | Error and failure case analysis; identification of normal-looking ECGs with disease labels | Model reliability assessment | Failure case documentation with reasoning |
| Week 9 | Consolidation of experiments; refinement of models and explanations | Strengthen results | Finalized figures, tables, and analyses |
| Week 10–12 | Manuscript preparation support: results organization, discussion inputs, limitations | Paper readiness | Journal-quality experimental material |

## Outcome at Project Completion

At the end of the project, the student will have developed a strong biomedical and computational understanding of pediatric ECG analysis, produced interpretable AI-based disease detection results, and contributed substantially to a research study suitable for submission to a high-quality (Q1) journal. The project emphasizes scientific reasoning, explainability, and clinical relevance rather than mere model accuracy, aligning with current expectations in medical AI research.

## Weekly Breakdown (Very Important)

### Week 0 (Orientation – Mandatory)

Goal: Conceptual grounding, no coding.

Ask her to go through:

- What is ECG?

- What are P, QRS, T waves?

- How myocarditis / congenital heart disease affects ECG (high-level)

Deliverable:

- 1–2 page handwritten or typed explanation

- No AI tools here

_________________________________________________________________

### Week 1 – Dataset Familiarization

Goal: Remove fear of data.

Ask her to:

- Download dataset

- Open one ECG signal

- Plot one lead

- Identify P, QRS, T visually

What she must learn:

- What is a lead?

- Why pediatric ECG differs from adults

- What labels exist (disease vs ECG statements)

Deliverable:

- Notebook with:

  - One ECG plotted

  - One disease label explained in her own words

_________________________________________________________________

### Week 2 – Signal Understanding (No ML yet)

Goal: Biomedical interpretation.

Tasks:

- Plot ECG from:

  - Healthy child

  - Child with one disease (you assign which)

- Compare waveform visually

Ask her to read:

- “Normal pediatric ECG vs abnormal ECG” (1–2 papers only)

Deliverable:

- Side-by-side ECG plots

- Written observation (not ML output)

_________________________________________________________________

### Week 3 – Feature Awareness (Still No Deep Learning)

Goal: Build intuition.

Ask her to:

- Extract:

  - Heart rate

  - RR interval

  - QRS duration (using library)

- Explain:

  - Why these matter medically

AI tools allowed:

- Yes (for coding only)

Deliverable:

- Table of extracted features

- One paragraph biomedical explanation

_________________________________________________________________

### Week 4 – First ML Model (Black Box Allowed)

Goal: Confidence building.

You decide:

- Binary classification (Disease vs Non-disease)

- One disease only

Ask her to:

- Train a simple CNN (even AI-generated)

- Report accuracy, confusion matrix

Critical instruction:

“Do not celebrate accuracy. We only observe behavior.”

Deliverable:

- Metrics

- Confusion matrix

- Short reflection

_________________________________________________________________

### Week 5 – Explainable AI (Core Contribution)

Goal: Shift from coding to science.

Ask her to:

- Apply:

  - Saliency map or Grad-CAM

- Overlay explanation on ECG

Key question she must answer:

“Which ECG region influenced the decision?”

Deliverable:

- Explained ECG plots

- Visual interpretation

_________________________________________________________________

### Week 6 – Age-Wise Analysis

Goal: Pediatric uniqueness.

Tasks:

- Split data into 2–3 age groups

- Repeat inference

- Compare explanations

Deliverable:

- Age-wise comparison plots

- Observation notes

___________________________________________

### Week 7 – Error & Failure Analysis

Goal: Reviewer-proofing.

Ask her to:

- Find cases where:

  - Disease ECG looks normal

  - Model fails

- Explain why (clinically)

Deliverable:

- Failure case discussion

- Screenshots + reasoning

___________________________________________

### Week 8 – Consolidation

Goal: Paper-ready material.

She compiles:

- Figures

- Tables

- Methods flowchart

- Explanation visuals

You take over:

- Writing abstract

- Positioning novelty

- Journal targeting